## Slide 1
DACS
When Calibration Data Matters
A Cross-Format Sensitivity Study for Quantized Fine-Tuned LLMs
Deepank Dixit | Optum AI Research | April 2026
🎯 Target: EMNLP 2026 — May 25 Deadline
$33.30
spent on Activity 0
83,000
training examples
61%
perplexity reduction
~$8
remaining GPU cost
6 weeks
to EMNLP deadline
40–70%
Findings (now→w/Act 3+4)
CONFIDENTIAL · Manager Briefing · Not for Distribution

## Slide 2
The Question: When Does Calibration Data Matter for Quantized Fine-Tuned LLMs?
Sensitivity varies sharply across quantization formats — and the map matters
The Deployment Pipeline
1
Fine-Tune on Domain Data
Llama-3.1-8B trained on 83K cybersecurity examples (CVE records, threat intelligence Q&A) using QLoRA. Result: perplexity 5.22 → 2.04 (61% drop).
2
Merge Adapter into Base Model
LoRA adapter matrices mathematically merged back into the 16GB FP16 model. Produces a standard checkpoint any inference server can load.
3
Quantize for Deployment ← THE AXIS WE STUDY
Every quantization tool (AWQ, SmoothQuant, FP8) needs a calibration dataset to set compression boundaries. Default: Wikipedia / C4 (generic web text). But the model was trained on cybersecurity text — not Wikipedia. The calibration data observes the WRONG activation distribution. Quantization ranges are set incorrectly. Domain accuracy drops.
4
Serve Efficiently (broken path)
Deployment outcome depends on (format × calibration) interaction. Our study maps which pairs are safe and which fail catastrophically.
Why This Matters
Fine-tuning concentrates weight changes in specific layers (the LoRA-adapted attention and MLP projections). Those layers now activate very differently on domain text vs. Wikipedia. Technical tokens like 'CVE', 'buffer overflow', 'MITRE ATT&CK' fire strong, domain-specific activation patterns that generic calibration never sees. Calibration on Wikipedia sets quantization ranges for Wikipedia-shaped activations. But at inference, the model processes cybersecurity text — and activations look completely different. Ranges are wrong. Accuracy suffers. The empirical finding: calibration sensitivity is format-dependent and cross-domain. FP8 is insensitive (0.00pp across all 3 domains). AWQ is mildly sensitive (0.30–1.03pp). SmoothQuant is critical: 9.31pp cyber, 2.41pp medical, 1.80pp code — with C2 self-calibration causing catastrophic regression. Hierarchy FP8 < AWQ < SQ is universal.
OPEN QUESTION
Williams ACL 2024 established calibration matters on base models. Williams NAACL 2025 showed self-calibration is safe on base models. MixCal (EACL 2026) proposes domain calibration for GPTQ. No prior work has mapped sensitivity across AWQ/SQ/FP8 on a domain fine-tuned LLM or identified the SQ self-calibration failure mode.

## Slide 3
Literature Review: What Exists — and What's Missing
Full review of ACL, EMNLP, NAACL, MLSys, NeurIPS through March 2026
CLOSEST PRIOR WORK
Williams & Aletras — ACL 2024
"On the Impact of Calibration Data in Post-Training Quantization and Pruning"
First paper to study calibration data choice for LLM quantization. Tested WikiText, C4, PTB, domain-adjacent data on standard base models (Llama, Mistral, OPT). Found calibration data does matter.
CRITICAL GAP: Only tested BASE models — no domain fine-tuning applied. The effect of LoRA/SFT on calibration sensitivity was never studied.
DIRECT PREDECESSOR
Williams, Chrysostomou & Aletras — NAACL 2025
"Self-Calibration for Language Model Quantization and Pruning"
Follow-on: if calibration data matters, eliminate external data dependency. Model generates its own synthetic completions for calibration. Matches or beats best generic calibration on standard benchmarks.
CRITICAL GAP: Again, only base models tested. Self-calibration for domain fine-tuned models — and whether model-generated text reproduces domain activation patterns — was never studied.
QUANTIZATION METHOD
AWQ (Lin et al.) — MLSys 2024 Best Paper
"AWQ: Activation-aware Weight Quantization for LLM Compression and Acceleration"
State-of-the-art W4A16 quantization. Protects high-salience weight channels via activation magnitude observation during calibration. Default calibration: WikiText-2 (512 samples).
ROLE: AWQ is one of three formats we test. Sensitivity: ~0.3pp MMLU, ~0.8pp WMDP across C1/C2/C3.
QUANTIZATION METHOD
SmoothQuant (Xiao et al.) — ICML 2023
"SmoothQuant: Accurate and Efficient Post-Training Quantization for LLMs"
Enables W8A8 quantization by smoothing activation outliers via mathematically equivalent per-channel scaling. Widely deployed in production. Default calibration: C4.
ROLE: SmoothQuant is the calibration-critical format. Sensitivity: 9.31pp MMLU spread, with catastrophic C2 self-calibration failure.
✦ THE OPEN QUESTION:
No paper has studied how domain fine-tuning (LoRA/SFT) changes PTQ calibration sensitivity, nor whether domain-matched calibration data recovers accuracy loss. No prior work has mapped sensitivity across AWQ/SQ/FP8 for domain fine-tuned LLMs or identified the SmoothQuant self-calibration failure mode on fine-tuned models.

## Slide 4
DACS: When Calibration Data Matters — The Solution
A sensitivity study, not a method proposal. Three honest contributions.
What Changes
Replace the calibration dataset.
That's it. One line of code change.
BEFORE (Standard Industry Practice)
calibration_data = load_wikitext(n=512) model_quantized = awq.quantize(model, calibration_data)
AFTER (DACS — proposed)
calibration_data = sample_sft_corpus(n=512) # ← DACS model_quantized = awq.quantize(model, calibration_data)
The Three-Way Test
C1
Generic (WikiText)
Industry standard. Baseline from Williams ACL 2024.
C2
Self-Calibration
Model generates own text. Baseline from Williams NAACL 2025.
C3
DACS (Proposed)
512 samples from fine-tuning corpus. Our method.
3 Honest Contributions
1
Format-Dependent Sensitivity Hierarchy
Cross-format characterization: FP8 is calibration-agnostic (0.00pp MMLU), AWQ mildly sensitive (≤0.3pp), SmoothQuant highly sensitive (9.31pp). Order is mechanistically predictable from each format's calibration dependence.
2
SmoothQuant Self-Calibration Failure Mode
Self-generated calibration causes a 9.31pp MMLU regression under SQ INT8 on fine-tuned models. Mechanism: activation-range underestimation during narrow autoregressive decoding. Qualifies Williams NAACL 2025's 'self-cal is safe' result: not safe for joint W/A quantization on fine-tuned models.
3
Practitioner Decision Surface
Use FP8 when hardware allows (calibration-agnostic). For AWQ, domain calibration gives a small consistent gain (+0.55pp WMDP, +0.22pp MMLU). For SmoothQuant, avoid self-generated calibration at all costs; treat calibration choice as deployment-critical.
4

## Slide 5
Experiment Plan: 7 Activities, ~50 GPU Hours, Under $31
All experiments on a single A10G GPU (24GB VRAM). No distributed training. All code already partially written.
Activity
Description
Status
GPU hrs
Days
Cost
Output / Benchmark
Activity 0
QLoRA Fine-Tune — 83K cybersecurity examples (COMPLETE)
✅ DONE
17.87h
—
$33.30
LoRA adapter | Perplexity 5.22 → 2.04 (61%)
Activity 1
Adapter Merge + FP16 Baseline Evaluation
✅ DONE
1h
Day 1
$0.75
Merged FP16 model | FP16 baseline: WMDP-Cyber ~44-46%, MMLU ~63-65%
Act. 2A/B/C
3-Way Calibration Experiment: Generic (C1) vs. Self (C2) vs. DACS (C3) — COMPLETE ✓
✅ DONE
10h
Days 2–4
$7.50
9 models evaluated: AWQ/SQ/FP8 × C1/C2/C3 | WMDP-Cyber + MMLU benchmarked
Activity 3
Multi-Domain Extension: Medical ✅ DONE | Code ✅ DONE (Apr 14, 2026)
✅ DONE
15h
Days 5–10
$11.25
Test if format sensitivity hierarchy generalizes across domains
Activity 4
Activation-Distribution Diagnostic (KL-div, per-layer)
⏳ TODO
5h
Days 11–13
$3.75
Per-layer KL | Validates SQ C2 mechanism + predictive metric
Activity 5
Evaluation Harness: CyberSecEval4, MMLU, MedQA
⏳ TODO
2h
Parallel
$1.50
Bootstrap CIs + automated benchmark pipeline for all configs
Activity 6
Ablation Studies: calibration size, LoRA rank, domain proximity
⏳ TODO
8h
Days 14–18
$6.00
Calibration size, LoRA rank, domain proximity ablations
Activity 7
Figures (×4) in paper ✅ | Tables in paper ✅ | Code eval ✅ DONE | Results committed d1ee399
✅ DONE
0h
Days 19–22
$0
3 figures created + wired into LaTeX ✅ | Code results section pending
TOTAL (Activities 1–7, excluding completed Activity 0)
~41 hrs
22 days
~$30.75
Full paper draft ready for peer-reviewed EMNLP 2026 submission

## Slide 6
Activity 3 Complete — 3-Domain Sensitivity Map Confirmed
May 25, 2026 ARR Submission Deadline · 2–3 hours/day · Budapest, October 24–29
Week 1 Apr 1–6
✓ Acts. 0–2
Weeks 2–3 Apr 7–20
TODAY ← Apr 14
Weeks 3–4 Apr 14–27
Multi-Domain
Weeks 4–5 Apr 21–May 4
Ablations
Weeks 5–6 May 4–18
Writing
Week 7 May 18–25
SUBMIT ✓
Acts. 0-2 COMPLETE: fine-tune, FP16 baseline, 9 quantized models evaluated on WMDP-Cyber + MMLU.
Act. 3: COMPLETE ✓ — 3-domain hierarchy confirmed (Cyber 9.31pp | Medical 2.41pp | Code 1.80pp SQ C2 regression; FP8 flat across all 3). Paper updated, fig3 (3-panel) + fig4 (summary chart) added.
Act. 4: activation-distribution analysis. Validates SQ C2 mechanism + diagnostic metric.
Acts. 5-6: bootstrap CIs, calibration-size and LoRA-rank ablations. Figures + tables.
All paper sections: Introduction, Method, Experiments, Related Work, Conclusion.
Final revision + ARR submission May 25. All authors register as reviewers by May 27.
The Three Asks
Ask 1 · HARD BLOCKER
GPU Access ✓
A10G (24GB) — ~41 hrs
Optum Azure ML / AWS SageMaker allocation, OR ~$37.50 on Lambda Cloud ($100 budget covers all experiments + buffer. Needed within 5 days to hit May 25 deadline.
Ask 2 · MOST IMPORTANT
Research Time
30–40% of working time
~2–3 hours focused work per day for 6 weeks. Remaining time stays on Army AI Tutor deliverables. If only 15–20% available → AAAI 2027 (Aug 1) becomes primary target.
Ask 3 · NICE TO HAVE
O'Reilly Subscription
~$500/yr
PyTorch internals, LLM deployment guides, quantization deep-dives. Check if Optum already has enterprise agreement. Can work without it — public arXiv papers sufficient.
Acceptance Probability
EMNLP 2026 Main
35–40% with Act3 complete
EMNLP 2026 Findings
60–65% with Act3 complete
BlackboxNLP 2026
75–85%
ENLSP @ NeurIPS 2026
65–75%
The gap is confirmed. The experiments cost < $31. The infrastructure is partially built. A 15–40% shot at a named A* publication is worth the attempt.
Deepank Dixit | Optum AI Research | April 2026